## Cover
AEROSPACE SOURCING RFQ TRACKER
Production-Grade Request for Quotation Management System
| VERSION |  | 2.0
| TOOL TYPE |  | RFQ Lifecycle Management
| AUDIENCE |  | Aerospace Sourcing & Procurement
| FORMAT |  | Microsoft Excel (.xlsx) — No Macros Required
| UPDATED |  | March 02, 2026
WORKBOOK CONTENTS
| Executive Summary | Portfolio-level KPIs and spend overview for leadership
| RFQ Tracker | Primary data entry — full RFQ lifecycle from issue to award
| Bid Comparison | Side-by-side supplier quote analysis per RFQ
| Supplier Scorecard | Auto-calculated supplier performance metrics
| Analytics Dashboard | KPIs, cycle time trends, commodity and spend breakdown
| Pipeline View | Monthly RFQ pipeline heat map by issue and due date
| Settings | Org name, SLA targets, fiscal year — drives all formulas
| Instructions | User guide and field definitions
Built for Aerospace Sourcing Professionals • Not connected to ERP/MRP • For portfolio demonstration

## Executive Summary
EXECUTIVE SUMMARY
RFQ Portfolio Health at a Glance
PORTFOLIO KPIs
TOTAL RFQs | OPEN | OVERDUE | AVG CYCLE TIME | SAVINGS REALIZED | SLA COMPLIANCE
60 | 25 | 3 | 38.1875 | 42840 | 10.67%
PRIORITY BREAKDOWN
CRITICAL | HIGH | MEDIUM | LOW | CLOSED
17 | 21 | 12 | 10 | 32
ITEMS REQUIRING ATTENTION
Status | RFQ Number | Part Description | Program | Priority | Supplier
Overdue and At Risk RFQs auto-populate here. Filter the RFQ Tracker tab by SLA Flag = "OVERDUE" or "AT RISK" to see current items.
SPEND SUMMARY
Total Target Spend | 1679400
Total Awarded Spend | 1284160
Net Savings | 42840
Sole Source Awards | 13
Competitive Awards | 24
Over-Target Rate | 9.375%
CYCLE TIME BY COMMODITY (AVG DAYS)
Commodity | Avg Cycle Time
Machined Parts | 37.6
Fasteners | 35
Composites | 40
Bearings | 34
Raw Material | 39
Actuation | 40
Forgings | 38.3333
Seals/Gaskets | -
All metrics are formula-driven from the RFQ Tracker tab. This summary auto-updates as RFQ data is entered or modified.
All supplier names, part numbers, and values are synthetic and illustrative only.

## RFQ Tracker
AEROSPACE RFQ TRACKER — v2.0
OPEN RFQs |  | OVERDUE |  | AT RISK (≤3 days) |  | AVG CYCLE TIME |  | RESPONSE RATE |  | SAVINGS REALIZED |  | SOLE SOURCE (AWARDS) %
25 |  | 3 |  | 5 |  | 38.2 days |  | 73% |  | 14700 |  | 25%
CRITICAL |  | HIGH |  | MEDIUM |  | LOW |  | CLOSED/AWARDED |  | CANCELLED |  | SLA BREACHES
17 |  | 21 |  | 12 |  | 10 |  | 32 |  | 2 |  | 0
# | RFQ Number | Part Number | Part Description | Program / Project | Commodity Code | Priority | Sole Source | Supplier Contacted | RFQ Issue Date | Response Due Date | Days Until Due | SLA Flag | Responses Received | # Quotes Received | Target Price ($) | Lowest Quote ($) | 2nd Low Quote ($) | Savings vs Target ($) | Savings vs Target (%) | Awarded Supplier | Award Date | Cycle Time (days) | SLA Met? | Status | Notes | Quote Sufficiency
1 | RFQ-2025-001 | AMS-4928-A | Ti-6Al-4V Machined Bracket | F-35 Lot 17 | Machined Parts | High | N | Vanguard Machining LLC | 2026-01-16 | 2026-02-15 |  |  | Y | 3 | 13000 | 12400 | 13800 | 600 | 4.615% | Vanguard Machining LLC | 2026-02-25 | 40 | Yes | Closed | Award below target. Solid 3-quote competition. | LOW
2 | RFQ-2025-002 | HEX-7741-B | Hex Head Bolt MS21250 (Qty 500) | CH-47 Support | Fasteners | Low | N | Fastener World | 2026-01-23 | 2026-02-20 |  |  | Y | 4 | 2000 | 1850 | 2100 | 150 | 7.5% | Fastener World | 2026-02-27 | 35 | Yes | Closed | Standard catalog item, excellent pricing. | LOW
3 | RFQ-2025-003 | CMP-0012-C | Composite Skin Panel Assy | B-21 PDR | Composites | Critical | N | AeroComposites Inc | 2026-01-31 | 2026-03-07 | 0 | AT RISK | Y | 2 | 90000 | 88500 | 94200 | 1500 | 1.667% |  |  |  |  | Open | Only 2 quotes received — consider expanding supplier base.
4 | RFQ-2025-004 | BRG-3310-D | Angular Contact Bearing 35mm | UH-60 Overhaul | Bearings | High | N | Atlas Bearing Corp | 2026-02-05 | 2026-02-28 | -7 | OVERDUE | N |  | 4500 | [8 empty] | Open | Follow up with SKF — no response yet.
5 | RFQ-2025-005 | SLV-8821-E | Aluminum Sleeving AS4373 | General Stock | Raw Material | Medium | N | Metals Direct | 2026-02-10 | 2026-03-10 | 3 | AT RISK | Y | 3 | 3500 | 3200 | 3750 | 300 | 8.571% |  |  |  |  | Open
6 | RFQ-2025-006 | ACT-5512-F | Electromechanical Actuator | V-22 Mod | Actuation | Critical | Y | Apex Actuators Inc | 2026-01-01 | 2026-01-31 |  |  | Y | 1 | 130000 | 145000 |  | -15000 | -11.54% | Apex Actuators Inc | 2026-02-10 | 40 | Yes | Closed | Sole source — OEM only. Justification on file. | LOW
7 | RFQ-2025-007 | HSS-2290-G | High-Strength Steel Forgings | F-35 Lot 17 | Forgings | High | N | Precision Forge Co | 2026-01-11 | 2026-02-10 |  |  | Y | 3 | 36000 | 34500 | 38000 | 1500 | 4.167% | Precision Forge Co | 2026-02-20 | 40 | Yes | Closed |  | LOW
8 | RFQ-2025-008 | SLR-4490-H | Seals & O-Ring Kit (AS568) | MRO Stock | Seals/Gaskets | Low | N | Delta Seal Systems | 2026-02-15 | 2026-03-14 | 7 | OK | N |  | 800 | [8 empty] | Open
9 | RFQ-2025-009 | WRG-6610-I | Wire Harness Assembly Assy | AH-64 Mod | Electrical | High | N | Conduit Aero Corp | 2026-02-20 | 2026-03-22 | 15 | OK | Y | 2 | 24000 | 22800 | 25600 | 1200 | 5% |  |  |  |  | Open | Two quotes in hand; awaiting third.
10 | RFQ-2025-010 | GBX-1100-J | Gearbox Housing Casting | T700 Engine | Castings | Critical | N | Summit Castings LLC | 2026-01-06 | 2026-02-05 |  |  | Y | 4 | 70000 | 67200 | 71000 | 2800 | 4% | Summit Castings LLC | 2026-02-15 | 40 | Yes | Closed | Best value; passed NDI inspection. | LOW
11 | RFQ-2025-011 | FLT-9921-K | Fuel Line Assembly SS Flex | CH-47 Support | Fluid Systems | Medium | N | FlexLine Corp | 2026-02-22 | 2026-03-27 | 20 | OK | N |  | 5500 | [8 empty] | Open
12 | RFQ-2025-012 | NUT-3301-L | Prevailing Torque Nut MS21042 | General Stock | Fasteners | Low | N | AeroFastener Co | 2026-01-26 | 2026-02-25 |  |  | Y | 5 | 750 | 620 | 710 | 130 | 17.33% | AeroFastener Co | 2026-03-04 | 37 | Yes | Closed | 5 competitive bids — best market response this quarter. | LOW
13 | RFQ-2025-013 | PCB-7700-M | Avionics PCB Assembly | B-21 PDR | Avionics | Critical | Y | Northway Avionics | 2026-02-25 | 2026-04-01 | 25 | OK | N |  | 18000 | [8 empty] | Open | Sole source OEM. FAR 6.302-1 applies.
14 | RFQ-2025-014 | TIT-5500-N | Titanium Bar Stock AMS4928 | F-35 Lot 17 | Raw Material | High | N | Pacific Alloy Supply | 2026-01-19 | 2026-02-18 |  |  | Y | 3 | 9800 | 9100 | 10400 | 700 | 7.143% | Pacific Alloy Supply | 2026-02-26 | 38 | Yes | Closed |  | LOW
15 | RFQ-2025-015 | SHK-2200-O | Landing Gear Shock Strut | V-22 Mod | Landing Gear | Critical | N | Stratos Landing Systems | 2026-02-27 | 2026-04-06 | 30 | OK | N |  | 52000 | [8 empty] | Open | Critical path item — expedite response.
16 | RFQ-2025-016 | PIN-4401-A | Clevis Pin AN392 (Qty 200) | General Stock | Fasteners | Low | N | AeroFastener Co | 2025-12-30 | 2026-01-29 |  |  | Y | 4 | 500 | 480 | 530 | 20 | 4% | AeroFastener Co | 2026-02-08 | 40 | Yes | Closed |  | LOW
17 | RFQ-2025-017 | HYD-3320-B | Hydraulic Manifold Block | AH-64 Mod | Fluid Systems | High | N | Delta Seal Systems | 2026-01-13 | 2026-02-12 |  |  | Y | 2 | 29000 | 28500 | 31200 | 500 | 1.724% | Delta Seal Systems | 2026-02-22 | 40 | Yes | Closed | Only 2 quotes — document per policy. | LOW
18 | RFQ-2025-018 | ALU-7710-C | 6061-T6 Aluminum Plate (10 sheets) | General Stock | Raw Material | Low | N | Metals Direct | 2025-12-22 | 2026-01-21 |  |  | Y | 5 | 4800 | 4200 | 4650 | 600 | 12.5% | Metals Direct | 2026-01-31 | 40 | Yes | Closed | Best market price — 5 quotes. | LOW
19 | RFQ-2025-019 | SEN-1120-D | Pressure Transducer 0-3000 PSI | V-22 Mod | Sensors | Medium | N | Horizon Aero Systems | 2026-02-23 | 2026-03-30 | 23 | OK | N |  | 7200 | [8 empty] | Open
20 | RFQ-2025-020 | CBL-5530-E | Control Cable Assembly 3/16" | CH-47 Support | Mechanical | High | N | Cablewerks Inc | 2026-01-09 | 2026-02-08 |  |  | Y | 3 | 9500 | 8900 | 9700 | 600 | 6.316% | Cablewerks Inc | 2026-02-18 | 40 | Yes | Closed |  | LOW
21 | RFQ-2025-021 | INS-2210-F | Thermal Insulation Blanket Assy | B-21 PDR | Composites | Medium | N | UTL Aerotech | 2026-02-26 | 2026-04-11 | 35 | OK | N |  | 14000 | [8 empty] | Open | RFQ issued — awaiting initial response.
22 | RFQ-2025-022 | TRQ-8840-G | Torque Tube Assy Titanium | F-35 Lot 17 | Machined Parts | Critical | N | Vanguard Machining LLC | 2025-12-02 | 2026-01-01 |  |  | Y | 3 | 21000 | 19800 | 22100 | 1200 | 5.714% | Vanguard Machining LLC | 2026-01-11 | 40 | Yes | Closed | Critical path — expedited award. | LOW
23 | RFQ-2025-023 | NOS-6610-H | Nose Fairing Fiberglass | UH-60 Overhaul | Composites | High | N | Vertex Composites | 2025-12-12 | 2026-01-11 |  |  | Y | 2 | 35000 | 33500 | 36800 | 1500 | 4.286% | Vertex Composites | 2026-01-21 | 40 | Yes | Closed |  | LOW
24 | RFQ-2025-024 | GRO-3310-I | Ground Strap Kit (Qty 50) | MRO Stock | Electrical | Low | N | Fastener World | 2026-02-15 | 2026-03-12 | 5 | OK | Y | 3 | 800 | 720 | 850 | 80 | 10% |  |  |  |  | Open | Quotes in. Evaluating.
25 | RFQ-2025-025 | VAL-7720-J | Check Valve 1/2 NPT SS | T700 Engine | Fluid Systems | Medium | N | Delta Seal Systems | 2025-11-22 | 2025-12-22 |  |  | Y | 4 | 3300 | 3100 | 3450 | 200 | 6.061% | Delta Seal Systems | 2026-01-01 | 40 | Yes | Closed |  | LOW
26 | RFQ-2025-026 | ROT-5540-K | Rotor Blade Root Fitting | CH-47 Support | Forgings | Critical | N | Summit Castings LLC | 2025-11-12 | 2025-12-12 |  |  | Y | 3 | 55000 | 52000 | 57500 | 3000 | 5.455% | Summit Castings LLC | 2025-12-22 | 40 | Yes | Closed | Below target — strong result. | LOW
27 | RFQ-2025-027 | WHL-9910-L | Main Wheel Assembly | UH-60 Overhaul | Landing Gear | High | N | Stratos Landing Systems | 2025-11-27 | 2025-12-27 |  |  | Y | 2 | 42000 | 41200 | 44500 | 800 | 1.905% | Stratos Landing Systems | 2026-01-06 | 40 | Yes | Closed | Only 2 approved sources. | LOW
28 | RFQ-2025-028 | SCR-1101-M | Machine Screw NAS1352 (Qty 1000) | General Stock | Fasteners | Low | N | AeroFastener Co | 2026-02-18 | 2026-03-17 | 10 | OK | Y | 5 | 450 | 390 | 430 | 60 | 13.33% |  |  |  |  | Open | 5 quotes received. Pending award.
29 | RFQ-2025-029 | CON-4420-N | Environmental Connector MIL-DTL-38999 | AH-64 Mod | Electrical | High | N | Conduit Aero Corp | 2026-02-24 | 2026-04-01 | 25 | OK | N |  | 11500 | [8 empty] | Open
30 | RFQ-2025-030 | FRM-6630-O | Aluminum Frame Weldment | V-22 Mod | Machined Parts | Medium | N | Vanguard Machining LLC | 2025-11-02 | 2025-12-02 |  |  | Y | 3 | 16500 | 15600 | 17200 | 900 | 5.455% | Vanguard Machining LLC | 2025-12-12 | 40 | Yes | Closed |  | LOW
31 | RFQ-2025-031 | BAT-2201-P | Aircraft Battery 24V 42AH | F-35 Lot 17 | Electrical | High | Y | Volt Aero Power | 2025-10-23 | 2025-11-22 |  |  | Y | 2 | 6000 | 5800 | 6400 | 200 | 3.333% | Volt Aero Power | 2025-12-02 | 40 | Yes | Closed | Sole source OEM. Only qualified supplier. | LOW
32 | RFQ-2025-032 | PMP-7730-Q | Hydraulic Pump 3000 PSI | CH-47 Support | Fluid Systems | Critical | Y | Ridgeline Fluid Power | 2025-10-13 | 2025-11-12 |  |  | Y | 2 | 70000 | 68500 | 73200 | 1500 | 2.143% | Ridgeline Fluid Power | 2025-11-22 | 40 | Yes | Closed | Sole source per MIL-SPEC QPL. | LOW
33 | RFQ-2025-033 | GKT-3301-R | Gasket Kit Engine Seal | T700 Engine | Seals/Gaskets | Medium | N | Delta Seal Systems | 2026-02-10 | 2026-03-07 | 0 | AT RISK | Y | 4 | 2100 | 1950 | 2200 | 150 | 7.143% |  |  |  |  | Open | 4 quotes received. Award pending.
34 | RFQ-2025-034 | ANT-5510-S | Antenna Assembly VHF/UHF | B-21 PDR | Avionics | High | Y | Northway Avionics | 2025-10-03 | 2025-11-02 |  |  | Y | 1 | 20000 | 22000 |  | -2000 | -10% | Northway Avionics | 2025-11-12 | 40 | Yes | Closed | Sole source — Type certified component. | LOW
35 | RFQ-2025-035 | SHF-8820-T | Drive Shaft Assy Steel | AH-64 Mod | Mechanical | Critical | N | Precision Forge Co | 2025-09-23 | 2025-10-23 |  |  | Y | 3 | 39000 | 37800 | 41000 | 1200 | 3.077% | Precision Forge Co | 2025-11-02 | 40 | Yes | Closed |  | LOW
36 | RFQ-2025-036 | FLX-2210-U | Flexible Coupling Assy | UH-60 Overhaul | Fluid Systems | Medium | N | FlexLine Corp | 2026-02-21 | 2026-03-24 | 17 | OK | N |  | 8800 | [8 empty] | Open
37 | RFQ-2025-037 | OXY-4410-V | Oxygen Regulator Assy | F-35 Lot 17 | Fluid Systems | High | Y | Skyline Safety Systems | 2025-09-13 | 2025-10-13 |  |  | Y | 2 | 15000 | 14200 | 15800 | 800 | 5.333% | Skyline Safety Systems | 2025-10-23 | 40 | Yes | Closed | Sole source — FAA/PMA only. | LOW
38 | RFQ-2025-038 | BRK-6620-W | Brake Assembly Multi-Disc | V-22 Mod | Landing Gear | Critical | N | Stratos Landing Systems | 2025-09-03 | 2025-10-03 |  |  | Y | 3 | 92000 | 89000 | 96500 | 3000 | 3.261% | Stratos Landing Systems | 2025-10-13 | 40 | Yes | Closed | Savings of $3k vs target. | LOW
39 | RFQ-2025-039 | ENG-1110-X | Engine Mount Bracket Ti | T700 Engine | Machined Parts | Critical | N | Vanguard Machining LLC | 2026-02-28 | 2026-04-16 | 40 | OK | N |  | 24000 | [8 empty] | Open | New requirement — RFQ just issued.
40 | RFQ-2025-040 | INV-3320-Y | DC/AC Power Inverter 400Hz | AH-64 Mod | Avionics | High | Y | Luminar Aero Electronics | 2025-08-24 | 2025-09-23 |  |  | Y | 2 | 32000 | 31500 | 34000 | 500 | 1.562% | Luminar Aero Electronics | 2025-10-03 | 40 | Yes | Closed | Sole source — qualified avionics supplier. | LOW
41 | RFQ-2025-041 | FRG-2210-A | Titanium Forging LH Rib | F-35 Lot 17 | Forgings | Critical | Y | Precision Forge Co | 2026-01-09 | 2026-02-08 |  |  | Y | 1 | 88000 | 88000 |  | 0 | 0% | Precision Forge Co | 2026-02-13 | 35 | Yes | Closed | Sole source — OEM-controlled process. Closed at target. | LOW
42 | RFQ-2025-042 | MCH-4450-B | Actuator Housing CNC | V-22 Mod | Machined Parts | High | N | Advanced Machining | 2026-01-16 | 2026-02-15 |  |  | Y | 4 | 32000 | 28500 | 29800 | 3500 | 10.94% | Advanced Machining | 2026-02-21 | 36 | Yes | Closed | 4 quotes — 10.9% savings vs target. Strong competition. | LOW
43 | RFQ-2025-043 | BRG-5520-C | Tapered Roller Bearing 50mm | UH-60 Overhaul | Bearings | Medium | N | Bearing Pro | 2026-01-22 | 2026-02-19 |  |  | Y | 2 | 6800 | 6650 | 7100 | 150 | 2.206% | Bearing Pro | 2026-02-25 | 34 | Yes | Closed | Only 2 quotes — LOW COMPETITION flag. Award within target. | LOW
44 | RFQ-2025-044 | ELC-3310-D | Avionics Power Supply 28V | AH-64 Mod | Avionics | High | N | Northway Avionics | 2026-01-04 | 2026-02-03 |  |  | Y | 3 | 45000 | 47200 | 49000 | -2200 | -4.889% | Northway Avionics | 2026-02-11 | 38 | Yes | Closed | Awarded over target — supply constraint. Flagged for next cycle renegotiation. | LOW
45 | RFQ-2025-045 | SEN-9900-E | Pressure Sensor MIL-Spec | T700 Engine | Sensors | Critical | Y | Horizon Aero Systems | 2026-01-26 | 2026-02-23 |  |  | Y | 1 | 12500 | 11900 |  | 600 | 4.8% | Horizon Aero Systems | 2026-02-28 | 33 | Yes | Closed | Sole source — OEM-controlled part. Award below target. | LOW
46 | RFQ-2025-046 | FST-1120-F | NAS1149 Washer Assortment Qty 2000 | General Stock | Fasteners | Low | N | Fastener World | 2026-02-03 | 2026-02-28 |  |  | Y | 5 | 3200 | 2750 | 2900 | 450 | 14.06% | Fastener World | 2026-03-03 | 28 | Yes | Closed | Catalog item — 5 quotes, 14% savings vs target. | LOW
47 | RFQ-2025-047 | HYD-8830-R | Flight Control Hydraulic Pump | UH-60 Overhaul | Fluid Systems | Critical | N | Ridgeline Fluid Power | 2026-01-14 | 2026-02-13 |  |  | Y | 3 | 95000 | 89500 | 93000 | 5500 | 5.789% | Ridgeline Fluid Power | 2026-02-19 | 36 | Yes | Closed | 3 quotes — 5.8% under target. Clean award. | LOW
48 | RFQ-2025-048 | MCH-3340-S | Gearbox Cover Plate CNC | CH-47 Support | Machined Parts | Medium | N | Apex Aero Parts | 2026-01-29 | 2026-02-25 |  |  | Y | 3 | 18500 | 17200 | 18000 | 1300 | 7.027% | Apex Aero Parts | 2026-03-02 | 32 | Yes | Closed | Competitive award — 3 quotes, 7% savings. | LOW
49 | RFQ-2025-049 | HYD-6630-G | Hydraulic Manifold Block | CH-47 Support | Fluid Systems | High | N | Ridgeline Fluid Power | 2026-01-19 | 2026-02-18 |  |  | N | 0 | [9 empty] | Cancelled | Program requirement dropped — cancelled before award.
50 | RFQ-2025-050 | SEL-2210-H | Shaft Seal Assembly Custom | F-35 Lot 17 | Seals/Gaskets | Medium | Y | Delta Seal Systems | 2026-02-13 | 2026-03-15 |  |  | N | 0 | [9 empty] | Cancelled | Design change eliminated requirement mid-RFQ.
51 | RFQ-2025-051 | CMP-3310-T | Composite Radome Assembly | F-35 Lot 17 | Composites | High | N | Composite Solutions | 2026-02-15 | 2026-04-19 |  |  | N | 0 | [9 empty] | On Hold | On hold — awaiting program office approval to proceed.
52 | RFQ-2025-052 | ACT-7710-I | Linear Actuator Assy | B-21 PDR | Actuation | Critical | Y | Apex Actuators Inc | 2026-02-08 | 2026-03-01 | -6 | OVERDUE | N | 0 | 67000 | [8 empty] | Open | OVERDUE — sole source, no response from Moog. Escalate immediately.
53 | RFQ-2025-053 | CMP-8820-J | Carbon Fiber Spar Cap | V-22 Mod | Composites | High | N | AeroComposites Inc | 2026-02-03 | 2026-03-03 | -4 | OVERDUE | Y | 1 | 54000 | 52000 |  | 2000 | 3.704% |  |  |  |  | Open | Overdue — only 1 quote. LOW COMPETITION. Expand outreach.
54 | RFQ-2025-054 | GKT-4430-K | O-Ring Kit MIL-P-5315 | T700 Engine | Seals/Gaskets | Medium | N | Delta Seal Systems | 2026-02-15 | 2026-03-07 | 0 | AT RISK | Y | 3 | 1800 | 1650 | 1750 | 150 | 8.333% |  |  |  |  | Open | AT RISK — due in 2 days. 3 quotes in hand, ready to award.
55 | RFQ-2025-055 | ENG-5540-L | Engine Mount Bushing Ti | F-35 Lot 17 | Machined Parts | Critical | Y | Vanguard Machining LLC | 2026-02-11 | 2026-03-08 | 1 | AT RISK | Y | 1 | 9500 | [8 empty] | Open | AT RISK — sole source, awaiting quote. Critical part.
56 | RFQ-2025-056 | RAW-3310-M | Titanium Bar Stock 6Al-4V | General Stock | Raw Material | Low | N | Titanium Supply Co | 2026-02-25 | 2026-03-17 | 10 | OK | N | 0 | 15000 | [8 empty] | Open | No supplier response yet — follow up required.
57 | RFQ-2025-057 | FOR-6610-N | Aluminum Forging Bulkhead | AH-64 Mod | Forgings | High | N | Stratos Landing Systems | 2026-02-23 | 2026-03-23 | 16 | OK | Y | 2 | 78000 | 74500 |  | 3500 | 4.487% |  |  |  |  | Open | 2 quotes — LOW COMPETITION. Target 3 minimum.
58 | RFQ-2025-058 | ELC-5510-P | Flight Computer Interface Card | B-21 PDR | Avionics | Critical | N | Northway Avionics | 2026-02-28 | 2026-04-09 | 33 | OK | Y | 1 | 125000 | [8 empty] | Open | Only 1 quote so far — pursuing 2 additional suppliers.
59 | RFQ-2025-059 | FST-9900-Q | Bolt MS21250-06028 Qty 1000 | General Stock | Fasteners | Low | N | AeroFastener Co | 2026-03-02 | 2026-04-02 | 26 | OK | N | 0 | [9 empty] | Open | Target price TBD — awaiting BOM confirmation.
60 | RFQ-2025-060 | SEN-4420-U | Fuel Flow Sensor MIL-Spec | T700 Engine | Sensors | High | Y | Horizon Aero Systems | 2026-02-27 | 2026-04-04 | 28 | OK | Y | 1 | 8800 | [8 empty] | Open | Sole source — OEM only. Awaiting quote.
ROW COLOR LEGEND
OVERDUE — Open RFQ past response due date. Immediate action required.
AT RISK — Response due within warning window (configurable in Settings).
PENDING — Open, awaiting supplier response, due date still future.
CLOSED — RFQ awarded and complete.
CANCELLED — RFQ voided. Retained for audit trail.

## Bid Comparison
BID COMPARISON MATRIX — Side-by-Side Supplier Analysis
Enter RFQ details below. One tab per comparison. Duplicate this sheet for additional RFQs.
RFQ Number: | RFQ-2025-003 |  |  | Part Number: | CMP-0012-C
Description: | Composite Skin Panel Assy |  |  | Program: | B-21 PDR
Target Price: | 90000 |  |  | Issue Date: | 2026-01-31
Commodity: | Composites |  |  | Due Date: | 2026-03-07
EVALUATION CRITERIA |  | SUPPLIER 1 | SUPPLIER 2 | SUPPLIER 3 | SUPPLIER 4 | SUPPLIER 5 | NOTES
Supplier Name |  | AeroComposites Inc | Vertex Composites
Quoted Price ($) |  | 88500 | 94200
Lead Time |  | 45 days | 60 days
Quality Certification |  | AS9100D | AS9100D
Previous Awards (Y/N) |  | Y | Y
On-Time Delivery Rating |  | 98% | 95%
Technical Exceptions |  | None | Minor notes
Terms (Net) |  | Net 30 | Net 30
Supplier Notes |  | Quoted per drawing rev C | Lead time concern flagged
Variance vs Target ($) |  | -1500 | 4200
Variance vs Target (%) |  | -1.667% | 4.667%
LOWEST QUOTE? |  | ✓ LOWEST
SOURCING RECOMMENDATION
Recommend award to AeroComposites Inc at $88,500 — lowest compliant bid, $1,500 (1.7%) below target. AS9100D certified, no technical exceptions. Competitive lead time of 45 days meets program schedule.

## Supplier Scorecard
SUPPLIER PERFORMANCE SCORECARD — Auto-calculated from RFQ Tracker
Metrics are automatically calculated from the RFQ Tracker sheet. Add supplier names below to track performance.
Supplier Name | RFQs Sent | Quotes Received | Response Rate | Awards Won | Win Rate | Avg Lowest Quote ($) | Performance Rating
Vanguard Machining LLC | 5 | 4 | 80% | 3 | 75% | 15933.3333 | Strong
Fastener World | 3 | 3 | 100% | 2 | 66.67% | 1773.3333 | Strong
AeroComposites Inc | 2 | 2 | 100% | 0 | 0% | 70250 | Responsive
Atlas Bearing Corp | 1 | 0 | 0% | 0 |  |  | Follow Up
Metals Direct | 2 | 2 | 100% | 1 | 50% | 3700 | Strong
Apex Actuators Inc | 2 | 1 | 50% | 1 | 100% | 145000 | Follow Up
Precision Forge Co | 3 | 3 | 100% | 3 | 100% | 53433.3333 | Strong
Delta Seal Systems | 6 | 4 | 66.67% | 2 | 50% | 8800 | Strong
Conduit Aero Corp | 2 | 1 | 50% | 0 | 0% | 22800 | Follow Up
Summit Castings LLC | 2 | 2 | 100% | 2 | 100% | 59600 | Strong
FlexLine Corp | 2 | 0 | 0% | 0 |  |  | Follow Up
AeroFastener Co | 4 | 3 | 75% | 2 | 66.67% | 496.6667 | Strong
Northway Avionics | 4 | 3 | 75% | 2 | 66.67% | 34600 | Strong
Pacific Alloy Supply | 1 | 1 | 100% | 1 | 100% | 9100 | Strong
Stratos Landing Systems | 4 | 3 | 75% | 2 | 66.67% | 68233.3333 | Strong

## Analytics
ANALYTICS DASHBOARD — Live Metrics from RFQ Tracker
VOLUME METRICS |  | CYCLE TIME METRICS |  | QUOTE & SAVINGS METRICS
Total RFQs Issued | 60 | Avg Cycle Time (days) | 38.1875 | Total Quotes Received | 119
Open RFQs | 25 | Min Cycle Time (days) | 0 | Avg Quotes per RFQ | 2.7045
Closed / Awarded | 32 | Max Cycle Time (days) | 40 | Response Rate | 73.33%
Cancelled | 2 | SLA Compliance Rate | 100% | Total Target Spend ($) | 1679400
Sole Source Awards | 8 | SLA Breaches (count) | 0 | Total Awarded Spend ($) | 1038450
Competitive Awards | 24 | SLA Target (days) | 30 | Total Savings vs Target ($) | 14700
PRIORITY BREAKDOWN |  | TOP COMMODITY GROUPS
Critical | 17 | Machined Parts | 7
High | 21 | Fasteners | 6
Medium | 12 | Composites | 5
Low | 10 | Bearings | 2
|  | Raw Material | 4
|  | Actuation | 2
|  | Forgings | 4
|  | Seals/Gaskets | 4
PORTFOLIO INTELLIGENCE — Second-Order Analytics
Identifies stalling RFQs, supplier miss patterns, over-target spend, and cycle time by commodity.
STALLING RFQs |  | SPEND vs TARGET |  | CYCLE TIME BY COMMODITY | Avg (days)
Open past SLA target | 0 | Closed RFQs over target price | 3 | Machined Parts | 37.6
Open — 0 quotes received | 3 | Closed RFQs at/under target | 29 | Fasteners | 35
Open — no supplier response | 13 | Over-target rate | 9.375% | Composites | 40
Critical parts currently Open | 7 | Total $ over target | -19200 | Bearings | 34
|  |  |  | Raw Material | 39
|  |  |  | Actuation | 40
|  |  |  | Forgings | 38.3333
|  |  |  | Seals/Gaskets | —

## Pipeline View
MONTHLY PIPELINE VIEW — RFQ Count by Issue Month
Counts auto-update from RFQ Tracker. Conditional formatting shows workload intensity — darker = more RFQs.
METRIC \ MONTH | Apr 2025 | May 2025 | Jun 2025 | Jul 2025 | Aug 2025 | Sep 2025 | Oct 2025 | Nov 2025 | Dec 2025 | Jan 2026 | Feb 2026 | Mar 2026
RFQs Issued | 0 | 0 | 0 | 0 | 1 | 3 | 3 | 4 | 4 | 18 | 26 | 1
Responses Due | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 3 | 4 | 5 | 18 | 17
Awards Made | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 5 | 15 | 3
Note: Months showing zero reflect periods prior to tracker adoption or months with no RFQ activity. Data populates automatically as RFQs are entered.

## Supplier Directory
APPROVED SUPPLIER DIRECTORY
Supplier Name | CAGE Code | Location | Commodity | AS9100 Cert? | Primary Contact | Contact Email | Approved?
Vanguard Machining LLC | 5NDB7 | Wichita, KS | Machined Parts | Y | John Smith | jsmith@vanguardmach.com | Y
AeroComposites Inc | 8XYZ2 | Huntington, WV | Composites | Y | Lisa Tran | ltran@aerocomp.com | Y
Fastener World | 3QRS9 | Burbank, CA | Fasteners | N | Mike Jones | mjones@fastenerwld.com | Y
Apex Actuators Inc | 1ABC4 | East Aurora, NY | Actuation | Y | Rachel Torres | rtorres@apexact.com | Y
Precision Forge Co | 7DEF1 | Cleveland, OH | Forgings | Y | Bob Harmon | bharmon@precforge.com | Y
Delta Seal Systems | 2GHI5 | Cleveland, OH | Seals/Fluid | Y | Kevin Park | kpark@deltaseal.com | Y
Conduit Aero Corp | 9JKL3 | St. Charles, MO | Electrical | Y | Mark Lane | mlane@conduitaero.com | Y
Summit Castings LLC | 4MNO8 | Mentor, OH | Castings | Y | Nora Grant | ngrant@summitcast.com | Y
FlexLine Corp | 6PQR2 | Springfield, MA | Fluid Systems | Y | Alex Dunn | adunn@flexline.com | Y
Northway Avionics | 0STU7 | Cedar Rapids, IA | Avionics | Y | Sam Reeves | sreeves@northwayav.com | Y
Pacific Alloy Supply | 5VWX1 | Albany, NY | Raw Material | N | Tony Voss | tvoss@pacificalloy.com | Y
Stratos Landing Systems | 8YZA4 | Longueuil, QC | Landing Gear | Y | Derek Simms | dsimms@stratoslanding.com | Y
AeroFastener Co | 3BCD6 | Torrance, CA | Fasteners | N | Gina Wu | gwu@aerofastener.com | Y
Atlas Bearing Corp | 7EFG9 | Gothenburg, SE | Bearings | Y | Brian Holt | bholt@atlasbearing.com | Y
Metals Direct | 2HIJ5 | Chicago, IL | Raw Material | N | Paul Grant | pgrant@metalsdirect.com | Y

## Settings
WORKBOOK SETTINGS — Edit values in column C
SETTING | VALUE ← EDIT HERE | NOTES
Organization Name | Your Organization | Appears on cover and dashboard
Sourcing Manager Name | Your Name | Optional — for tracking ownership
Fiscal Year Start Month | 10 | Enter month number (e.g. 10 = October for US DoD FY)
RFQ Cycle Time SLA (days) | 30 | Target max days from issue to award — drives SLA flag
Overdue Warning (days) | 3 | Days before due date to flag as 'At Risk' (amber)
Min Quotes Required | 3 | Minimum competitive bids target per RFQ
Default Currency | USD | For display reference only
Version | 2.0 | Do not edit
As-Of Date | 2026-03-07 | Freeze this date to lock metrics for a snapshot
Settings in column C are referenced by formulas throughout this workbook. Do not rename this sheet.

## Instructions
USER GUIDE — Aerospace RFQ Tracker v2.0
QUICK START
1 | Open the Settings sheet — Enter your organization name, SLA target (days), and overdue warning window. These values power all formulas.
2 | Enter RFQs in RFQ Tracker — Fill in one row per RFQ. Required fields: RFQ Number, Part Number, Supplier Contacted, Issue Date, Due Date, Priority, Status.
3 | Update status as RFQ progresses — Change Status from Open → Closed when awarded. Enter Award Date and Awarded Supplier. Cycle Time auto-calculates.
4 | Use Bid Comparison for awards — Duplicate the Bid Comparison sheet for each competitive award. Document all quotes received before making a recommendation.
5 | Check Analytics & Scorecard — Review weekly. The Supplier Scorecard tracks response rates and win rates per supplier automatically.
FIELD DEFINITIONS
RFQ Number | Unique identifier. Suggested format: RFQ-YYYY-NNN (e.g., RFQ-2025-001).
Priority | Critical = program-stopper / must-award immediately. High = urgent. Medium = standard. Low = stock/MRO.
Sole Source (Y/N) | Y = single approved supplier (OEM, proprietary, qualified only). Requires written justification per FAR 6.302.
SLA Flag | Auto-calculated. OVERDUE = past due date. AT RISK = within warning window. OK = on track.
Cycle Time | Automatically calculated: Award Date minus Issue Date. Blank until both dates are entered.
SLA Met? | Yes if Cycle Time ≤ SLA Target (set in Settings). No if it exceeded. Used for SLA compliance reporting.
Savings vs Target | Positive = came in under budget. Negative = exceeded target. Formula: Target Price minus Lowest Quote.
COLOR CODING
Red rows | OVERDUE: Open RFQ past its response due date. Take immediate action — call supplier, expedite, or escalate.
Amber rows | AT RISK: Due date within warning window (default 3 days, configurable in Settings).
Yellow rows | PENDING: Open RFQ, response not yet received, due date still in the future.
Green rows | CLOSED: RFQ awarded. No further action needed.
Grey rows | CANCELLED: RFQ voided. Retained for audit trail — do not delete.
BEST PRACTICES
Minimum 3 quotes | Set Settings!C10 to your organization's minimum. Dashboard tracks RFQs that fell short.
Sole source control | Every Y in the Sole Source column should have a corresponding written justification on file (FAR 6.302, DFARS 206).
Notes column | Use the Notes column for sourcing rationale, issues, or actions. This supports audit readiness.
Bid Comparison | Duplicate the Bid Comparison sheet for every competitive award. A complete bid tab is your source selection documentation.
Do not delete rows | Mark cancelled RFQs as 'Cancelled' rather than deleting. Preserved rows maintain the audit trail.
LIMITATIONS
No ERP integration | This tool is standalone. Data must be entered manually. It does not sync with SAP, Oracle, Costpoint, or other MRP/ERP systems.
No macro / VBA | This workbook uses only Excel formulas and conditional formatting. No VBA. Compatible with Excel 2016+ and Microsoft 365.
Row capacity | RFQ Tracker supports up to 300 RFQ rows. Archive completed RFQs to a separate file if nearing capacity.